## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Personel | Loss of team members | One or more team members drop the class | 2 | 4 | 4 | 32 | All team members | 2024-10-15 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
Personel | Schedule clashes (home and work life) | Scheduling conflicts resulting in difficulty finding time to meet | 5 | 3 | 4 | 12 | All team members | 2024-10-15 | Have set meeting times throughout the week and communicate via Discord if any conflicts arise and reschedule where necessary | We have been able to meet at the times agreed upon | Open
Communication | Duplicate work | Not clear assignment of tasks and multiple team members working on same task | 3 | 4 | 4 | 24 | Team Leader | 2024-10-15 | Clearly define tasks and assign task leaders. Communicate progressive updates through Discord, and take advantage of Git features to monitor repository updates. | There was some duplicate work with Docker as well as the creating the Architectural Diagram in Iteration 1. We will strive to communicate better to avoid this occurring in the upcoming iterations. | Open
Requirements | Unclear requirements | Jira ticket is not well-defined, leading to confusion and/or misaligned expectations | 3 | 4 | 4 | 24 | Requirements Leader | 2024-10-15 | Work to clearly define requirements, and keep requirements updated as project evolves. Remain flexible to communicate with team to eliminate points of confusion. | This has not been an issue so far | Open
Requirements | Scope creep | Additional features or requirements being added beyond the original plan, which leads to additional cost | 4 | 4 | 5 | 20 | Requirements Leader | 2024-10-15 | Estimate hours for every task and story item on an ongoing basis. Weigh against total potential hours for each iteration. | Similar features have been condensed and combined. Feature prioritization and necessity is reevaluated at each sprint | Open
Management | Improper planning | Inadequate or unrealistic scheduling, resource allocation, or task prioritization | 3 | 4 | 4 | 24 | Requirements Leader | 2024-10-08 | Open communication within team with ongoing feedback during planning process to ensure amount of work assigned is realistic | Sprints have been planned realistically and work has been assigned fairly | Closed
Technology competence | Not familiar with React | Insufficient experience or expertise with the React framework could lead to slower development | 3 | 3 | 4 | 36 | All team members | 2024-09-24 | Team members should individually upskill on React while also supporting each other in the learning process | All team members have upskilled in their own time | Closed
Technology competence | Not familiar with unit testing | Insufficient experience or expertise with unit testing could lead to slower development | 3 | 3 | 3 | 27 | All team members | 2024-10-08 | Team members should individually upskill on unti testing while also supporting each other in the learning process | All team members have upskilled in their own time | Closed
Technology competence | Not familiar with Git | Insufficient experience or expertise with Git could lead to slower development | 3 | 2 | 3 | 36 | All team members | 2024-09-24 | Team members should individually upskill on Git while also supporting each other in the learning process | All team members have upskilled in their own time | Closed
Design and implementation | Messy Code | It may be complicated to debug code. This is typcially due to poor structure | 3 | 2 | 4 | 48 | All team members | 2024-10-15 | Well documented code and useful comments so everything is easily understood | This has not been an issue so far | Open
Testing | Not enough testing | The number of bugs will increase if the software is not tested properly. | 3 | 4 | 4 | 24 | QA Leader | 2024-10-15 | Requiring test cases for each feature | This has not been an issue so far | Open
Integration and deployment | Not enough time for integration and deployment | This can lead to configuration issues, missing components, environment problems | 2 | 3 | 3 | 36 | Configuration Leader | 2024-10-03 | Set up configuration for automatic deployment with GitHub Actions | dev branch is auto-deployed every time a branch is merged into it | Closed
Integration and deployment | Hosting service | Need to have a servicable hosting service that is ideally free | 3 | 2 | 1 | 12 | Configuration Leader | 2024-09-26 | Research potential viable options that suits the scope of the project. Get a subscription if truly necessary | After initially testing with Heroku, it was decided to move forward with it due to already having it configured, despite the small paywall | Closed